## Sheet1
RIGHT PANEL
Test ID | Component | Tester | Date Tested | Test Conditions | Expected Results | Actual Results | Pass/Fail | Notes
R-001a | Alarm Unit | Beason, Curths, McAnulty | 2023.04.24 | Input Signal High | HMI Reports High Signal, Alarm Lights/Sound On | alarm activates correctly | Pass
R-001b |  | Beason, Curths, McAnulty | 2023.04.24 | Input Signal Low | HMI Reports Low Signal, Alarm Lights/Sound Off | alarm deactivates correctly | Pass
R-002a | HMI Screen | Beason, Curths, McAnulty | 2023.04.24 | System in ready state | State of system is accurately reported | HMI correctly reports PLC data points | Pass
R-002b |  | Beason, Curths, McAnulty | 2023.04.24 | System in ready state, input sent via panel | Input properly changes state of system | model state properly changes with user HMI input | Pass
R-003a | PIR Sensor | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled | Movement Sets Signal High, HMI Reports Signal High, Alarm Signal High, Signal Resets to Low after Delay | Movement triggers alarm, alarm resets after delay | Pass
R-003b |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Disabled | Movement Sets Signal High, HMI Reports Signal High, Alarm Signal Low, Signal Resets to Low after Delay | movement triggers sensor but not alarm | Pass
R-004a | IR Beam Sensor | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, No Obstruction | HMI Reports Correct State, Alarm Signal Low | alarm off, hmi correct | Pass
R-004b |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, Beam Obstructed | HMI Reports Correct State, Alarm Signal High | alarm triggered and resets when beam is no longer obstructed | Pass
R-004c |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Disabled, Beam Obstructed | HMI Reports Correct State, Alarm Signal Low | obstruction reported correctly, no alarm | Pass
R-005a | Magnetic Sensor | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, Switch Closed | HMI Reports Correct State, Alarm Signal Low | correct behavior observed | Pass
R-005b |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, Switch Open | HMI Reports Correct State, Alarm Signal High | switch state reported correctly, alarm triggered | Pass
R-005c |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Disabled, Switch Open | HMI Reports Correct State, Alarm Signal Low | switch state reported correctly, alarm not triggered | Pass
R-005a | Smart Lock | Beason, Curths, McAnulty | 2023.04.24 | Deadbolt Locked | HMI Reports Correct State, Model FD Signal Low | state properly reported | Pass
R-005b |  | Beason, Curths, McAnulty | 2023.04.24 | Deadbolt Unlocked | HMI Reports Correct State, Model FD Signal High | state properly reported | Pass
R-006a | RF Receiver | Beason, Curths, McAnulty | 2023.04.24 | Door Closed, Open Button Pressed | Door Moves to Fully Open Position, HMI Correct | door moves and stops at correct position, HMI properly reports state | Pass
R-006b |  | Beason, Curths, McAnulty | 2023.04.24 | Door Open, Closed Button Pressed | Door Moves to Fully Closed Position, HMI Correct | door moves and stops at correct position, HMI properly reports state | Pass
HOME MODEL
| Component | Tester | Date Tested | Test Conditions | Expected Results | Actual Results | Pass/Fail | Notes
H-001a | Front Door | Beason, Curths, McAnulty | 2023.04.24 | Input Signal Low | Solenoid Extended, Door Locked | solenoid properly extends when no signal is sent, door secured | Pass
H-001b |  | Beason, Curths, McAnulty | 2023.04.24 | Input Signal High | Solenoid Retracted, Door Unlocked | solenoid properly retracts with high signal, door can be opened | Pass
H-002a | Garage Door | Beason, Curths, McAnulty | 2023.04.24 | Door Closed | HMI Reports Door Closed | door state properly reported | Pass
H-002b |  | Beason, Curths, McAnulty | 2023.04.24 | Door Open | HMI Reports Door Open | door state properly reported | Pass
H-003a | L3 Magnetic Sensor | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, Switch Closed | HMI Reports Correct State, Alarm Signal Low | correct behavior observed | Pass
H-003b |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, Switch Open | HMI Reports Correct State, Alarm Signal High | switch state reported correctly, alarm triggered | Pass
H-003c |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Disabled, Switch Open | HMI Reports Correct State, Alarm Signal Low | switch state reported correctly, alarm not triggered | Pass
H-004a | L3 IR Beam Sensor | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, No Obstruction | HMI Reports Correct State, Alarm Signal Low | alarm off, hmi correct | Pass
H-004b |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled, Beam Obstructed | HMI Reports Correct State, Alarm Signal High | alarm triggered and resets when beam is no longer obstructed | Pass
H-004c |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Disabled, Beam Obstructed | HMI Reports Correct State, Alarm Signal Low | obstruction reported correctly, no alarm | Pass
H-005a | L2 PIR Sensor | Beason, Curths, McAnulty | 2023.04.24 | Alarm Enabled | Movement Sets Signal High, HMI Reports Signal High, Alarm Signal High, Signal Resets to Low after Delay | movement triggers alarm, alarm resets after delay | Pass
H-005b |  | Beason, Curths, McAnulty | 2023.04.24 | Alarm Disabled | Movement Sets Signal High, HMI Reports Signal High, Alarm Signal Low, Signal Resets to Low after Delay | movement triggers sensor but not alarm | Pass
H-006a | L2 LED Lighting | Beason, Curths, McAnulty | 2023.04.24 | White Output Signal High | White Lights Enabled | white properly activates | Pass
H-006b |  | Beason, Curths, McAnulty | 2023.04.24 | White Output Signal Low | White Lights Disabled | white properly deactivates | Pass
H-006c |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal High | Green Lights Enabled | green properly activates | Pass | Green lights only activate when alarm is enabled. Intended behavior.
H-006d |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal Low | Green Lights Disabled | green properly deactivates | Pass
H-006e |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal High, Alarm Low->High | Green Lights Disabled Following Alarm Trigger | green lights properly reset on alarm trigger | Pass
H-007a | L3 LED Lighting | Beason, Curths, McAnulty | 2023.04.24 | White Output Signal High | White Lights Enabled | white properly activates | Pass
H-007b |  | Beason, Curths, McAnulty | 2023.04.24 | White Output Signal Low | White Lights Disabled | white properly deactivates | Pass
H-007c |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal High | Green Lights Enabled | green properly activates | Pass | Green lights only activate when alarm is enabled. Intended behavior.
H-007d |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal Low | Green Lights Disabled | green properly deactivates | Pass
H-007e |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal High, Alarm Low->High | Green Lights Disabled Following Alarm Trigger | green lights properly reset on alarm trigger | Pass
H-008a | L1 LED Lighting | Beason, Curths, McAnulty | 2023.04.24 | White Output Signal High | White Lights Enabled | white properly activates | Pass
H-008b |  | Beason, Curths, McAnulty | 2023.04.24 | White Output Signal Low | White Lights Disabled | white properly deactivates | Pass
H-008c |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal High | Green Lights Enabled | green properly activates | Pass | green lights only activate when alarm is enabled. Intended behavior.
H-008d |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal Low | Green Lights Disabled | green properly deactivates | Pass
H-008e |  | Beason, Curths, McAnulty | 2023.04.24 | Green Output Signal High, Alarm Low->High | Green Lights Disabled Following Alarm Trigger | green lights properly reset on alarm trigger | Pass
H-009a | L1 Push Button | Beason, Curths, McAnulty | 2023.04.24 | Alarm Signal Low, Alarm Enabled, Button Pushed | Green Light Enabled | functioning correctly | Pass
H-010a | L2 Push Button | Beason, Curths, McAnulty | 2023.04.24 | Alarm Signal Low, Alarm Enabled, Button Pushed | Green Light Enabled | functioning correctly | Pass
| L3 Push Button | Beason, Curths, McAnulty | 2023.04.24 | Alarm Signal Low, Alarm Enabled, Button Pushed | Green Light Enabled | functioning correctly | Pass
CYBER
| Component | Tester | Date Tested | Test Conditions | Expected Results | Actual Results | Pass/Fail | Notes
C-001a | ARP Poisoning Attack | Beason, Curths, McAnulty | 2023.04.24 | System Vulnerable, Attack Deployed | Network Traffic Visible in Wireshark, Packet Data Viewable | Performed as Expected | Pass
C-002a | ARP Poisoning Defense | Beason, Curths, McAnulty | 2023.04.24 | System Hardened, Attack Deployed | No system traffic visible in Wireshark | Performed as Expected | Pass
C-003a | Packet Injection Attack | Beason, Curths, McAnulty | 2023.04.24 | System Vulnerable, Attack Deployed | Alarm System Bypassable on Each Floor, Buttons Properly Activate Green LED's for Each Floor | Performed as Expected | Pass | System not reset to clean state after attacks. Developed cleanup script to address issue and reverse tampering.
C-004a | Packet Injection Defense | Beason, Curths, McAnulty | 2023.04.24 | System Hardened, Attack Deployed | System Does Not Respond to Illegitimate Packets | Performed as Expected | Pass